“Making Rural Youth Employable: Our Dream”

-SPSC Vocational Education & Employment Facilitation Centre,

Nagapattinam

Project	:	Access to vocational education and employment facilitation for rural poor 		youth

Region	: 	Nagapattinam and Thiruvarur District Tamil Nadu, Karaikal District, 			Puduchery

Duration	: 	01.09.2014 - 31.12.2017

Target group	: 	The direct target group consists of 1.080 poor rural adolescents, who 		don’t have access to affordable, high-quality and demand-oriented 			vocational training. 600 adolescents will receive vocational training and 		480 adolescents will receive coaching. The indirect target group consists 		of parents of the trainees and stakeholders like members of the local 		communities and government institutions, local SHGs and employers as 		well as parent-teacher-associations. There is the potential to reach all the 		inhabitants within a 60-km-radius of Velankanni through the community 		radio, total 500.000 people.

Short description – targets and planned measures:

The main objective is to provide access to affordable, high-quality and demand-oriented vocational training for poor adolescents from a rural background in order to improve their chances to acquire a secure and well-paid job. This will contribute to improve the income and livelihood of the adolescents and their families. In the long run it will have a positive impact on a reduction of poverty, an increase of economic productivity and an improvement in social cohesion.

Planned measures:

Awareness raising: baseline study; community sensitization; cooperation with existing radio station and establishment of a new radio station; preparation of radio program

Vocational education center: modification and equipping the existing building; recruitment and training of educational staff; meeting with educational experts for organizational development and creation/ adaption of curricula; affiliation of courses; preparation of application process; establishment of catering service

Courses: running of vocational training center: vocational and coaching courses; financial support for poor trainees including insurance

Job facilitation: networking with employers and preparation of MoU; linking alumnis with banks and government schemes; establishment of alumni association

## Project Description

Overall Objective

Increase of income and improvement of livelihood of poor adolescents and their families in the rural districts of Nagapattinam, Thiruvarur and Karaikal through vocational education and job facilitation.

Project Objective

1.080 underprivileged adolescents from a rural background have access to affordable, high-quality and demand-oriented vocational education and secured job perspectives.

Activities

- The general public of the project area is aware of the importance of demand-oriented vocational training.

- Baseline study

- community sensitization

- Cooperation with existing radio station

- Establishment and licensing of own radio station: Radio Youth

- Radio program preparation

A Vocational Training Center is established and works in a sustainable way.

- Modification and Equipment of the building

- Meetings with educational experts in development of organization and preparation/ adjustment of curricula

- Recruitment and training of educational staff

- Affiliation of courses

- Application process

Adolescents have access to affordable, high-quality and demand-oriented vocational education and training courses.

- Vocational training courses (including English, computer skills and life skills)

6 vocational training courses will be set up and equipped with the following material

- Training courses

- Financial support for poor trainees including insurance

The graduates of the vocational training center have found a job or have started their own business.

- Linking graduated with employers and signing of MoUs

- Access to bank loans and governmental schemes

- Establishment of alumni club

Staff Team:

Chief Executive Officer, Monitoring and Evaluation cum Empoyment Facilitation Officer, Community Radio Coordinator, Enrollment Promoter, Accountant, Instructors (6), Tutors (2)

- Contact

- SPSC-Vocational Education and Employment Facilitation Centre

- No.2/11-C2, ECR Main Road, Palathadi, Velankanni – 611 111

- Nagapattinam Dt, Tamil Nadu, India

- Ph/Fax:+91-04365-264488

- Email: veef@peacetrust.in

- Internet: www.peacetrust.in 																		Dr.J.Paul Baskar Ph.D

- Chairman, Peace Trust